PREQAL INTEGRATED MANAGEMENT SYSTEM  ·  Controlled Document — Internal Use Only

SOP-06: Project Scoping & Delivery

Standard Operating Procedure

| Document No |  |
| --- | --- |
| Version | 1.0 |
| Effective Date | 2026-05-07 |
| Document Owner | Dr. Stefan Gravesande |
| ISO Reference |  |
| Related Documents |  |
| Classification | Internal — Controlled Document |

1. Purpose

To ensure every Preqal engagement is delivered consistently, on scope, on time, and to a standard that demonstrably solves the client's quality problem — with full traceability of all decisions, deliverables, and communications.

2. Scope

Applies from project kickoff (first meeting with client) through to submission of final deliverables. Covers all Preqal service types: Gap Analysis, QMS/IMS Development, ISO Certification Support, Training, National Framework Development.

3. Definitions

| Term | Definition |
| --- | --- |
| Kickoff | The first structured meeting between Preqal and the client — sets expectations, confirms scope, and establishes working rhythm |
| Gap Analysis | A systematic comparison of the client's current state against the requirements of a relevant standard (e.g., ISO 9001, ISO 22000, ISO 45001) |
| IMS | Integrated Management System — a unified framework combining multiple ISO standards |
| Deliverable | A specific, tangible output committed to in the contract (e.g., a documented procedure, a training session, a completed audit report) |
| Milestone | A key progress point agreed at kickoff (e.g., "Phase 1 complete: Gap Analysis Report submitted") |
| Sprint | A 1–2 week work cycle with defined tasks and a review at the end |

4. Roles & Responsibilities

🧑  Human Employee Roles

| Role | Responsibility | Type |
| --- | --- | --- |
| Dr. Gravesande | Leads all client-facing engagement; approves all deliverables; accountable for quality of output | Human Employee |
| Client Project Champion | Single point of contact on the client side; facilitates access to staff, documents, and processes | Human Employee |

🤖  Agentic Employee Roles

| Agent | Responsibility | Type |
| --- | --- | --- |
| Research Agent | Pulls relevant standard requirements, industry benchmarks, and regulatory context for the specific engagement | Agentic Employee |
| Documentation Agent | Drafts procedures, work instructions, and policy documents based on gap analysis findings and Dr. Gravesande's direction | Agentic Employee |
| Status Report Agent | Generates weekly status report (TPL-10) from project notes and milestone tracking; submits for Dr. Gravesande review before sending | Agentic Employee |

⚠  Agentic Note: No deliverable is sent to the client without Dr. Gravesande's review and approval. Agents DRAFT. Humans APPROVE and SEND.

5. Process Overview

Project delivery operates in four phases: **Kickoff → Diagnose → Build → Validate**. Each phase ends with a milestone deliverable and client sign-off. The CRM pipeline stage advances at each milestone. Weekly status reports keep the client informed and create accountability.

6. Inputs

- Completed onboarding file (from SOP-05)

- Signed contract with defined scope and milestones

- TPL-09 (Kickoff Agenda Template)

7. Procedure

◆  Phase 1: Kickoff

Step 1 — Prepare for Kickoff Meeting

1.1.  Review the full onboarding submission (FORM-02 data and uploaded documents).

1.2.  Prepare the Kickoff Agenda using TPL-09. Populate all variable fields:

- Client name, project name

- Meeting objectives (confirm scope, establish communication rhythm, agree milestones)

- Open questions from onboarding review

1.3.  Send the agenda to the client 48 hours before the meeting: *"Looking forward to our kickoff. Agenda attached — please flag anything you'd like to add."*

1.4.  Update CRM: `pipeline_stage` → `Scoping`.

Step 2 — Conduct Kickoff Meeting

2.1.  Open the meeting by confirming the overall goal: *"By the end of this engagement, [specific outcome from contract]. Today we confirm how we get there."*

2.2.  Walk through scope item by item — confirm client's understanding matches contract.

2.3.  Confirm the client's Project Champion and their availability.

2.4.  Agree communication rhythm: e.g., *"Weekly status report every Friday; milestone review calls at the end of each phase."*

2.5.  Agree milestone dates — write them down and share in the meeting summary email within 24 hours.

2.6.  Identify any immediate risks or constraints (e.g., "We have an audit in 6 weeks — can we prioritise the HACCP documentation?").

2.7.  Send meeting summary within 24 hours — include: agreed milestones, next steps, open actions with owners.

8. Outputs

- Completed deliverables as per contract (filed in Google Drive)

- Weekly status reports (sent to client)

- CRM updated at each milestone

- Handoff to SOP-07

9. Quality Controls & KPIs

| Metric | Target | Review Frequency |
| --- | --- | --- |
| Kickoff held within 5 business days of onboarding complete | 100% | Per project |
| Weekly status reports sent | 100% on schedule | Weekly |
| Milestone deliverables submitted on time | ≥ 90% | Per milestone |
| Client sign-off obtained at each phase | 100% | Per phase |
| Deliverables free of critical errors on first review | ≥ 85% | Per deliverable |

10. Non-Conformance Handling

Scope creep:: If client requests work outside the contracted scope, log the request. Assess whether it can be accommodated within existing budget/time. If not: prepare a Change Order (amendment to TPL-03) before commencing the additional work.

Missed milestone:: Log in REG-06. Identify cause (Preqal-side or client-side delay). Adjust the project plan and notify the client in writing within 24 hours of identifying the delay.